## Sheet1
S.# | Product | EM Name | Sprint Length | Total Dev Resources | Decision: 6th Sprint vs. 20% | Start Date | Status | Rationale | Blockers / Risks | QA POC | Dev Training Status | Notes / Follow-up | Metrics
1 | Sell Side OMS | Faizan Rahim Khan | 2 | 5 | 6th Sprint | 2025-11-17 |  | Initial Framework needs to be setup so it's better to start with 6th sprint. | Dev would require training. Training will be done before starting the automation. | Nida Yahya/Kashaf/Mubashir | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
2 | vTrader Client | Faizan Rahim Khan | 3 | 3 | 20% | 2025-09-02 |  |  | None | Nida Yahya | Completed |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
3 | SDK | Faizan Rahim Khan | 3 | 4 | 20% | 2025-09-23 |  |  | None | Mubashir Khan | Completed |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
4 | DAS | Faizan Rahim Khan |  |  | TBD | TBD |  | Currently, DAS is being manually tested. Going forward, we plan to automate DAS. | Since it does not have an interface, QA team would need Dev team to provide a library, wrapper or a utility that can be used to write the automation code. | Kashaf/Kamran | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
5 | vFlux | Murtaza | 2 | 3 (Shared resources) | 6th Sprint | 15th December 2025 |  | It's easier to manage a single dedicated sprint instead of every sprint. | None | Maryam Shakeel | Completed |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
6 | vCertify | Murtaza | 2 | 3 (1 dedicated, 2 shared) | 7th Sprint | 29th December 2025 |  | vFlux and vCertify sprints start at the same time and due to shared resources, we decided to take every 7th sprint for dedicated automation | None | Maryam Shakeel | Completed |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression): | Metrics Definition
7 | FCM | Murtaza | 2 | 5 (dedicated resources) | 6th Sprint | TBD |  | It's easier to manage a single dedicated sprint. We already are 90%+ in automation. | Dev would require training. Training will be done before starting the automation. | Maryam Shakeel | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression): | Automation Cadence Adoption | % of sprints where automation capacity was honored (6th sprint or 20%).
8 | New Account Opening and Customer Portal | Mazhar Karimi | 2 | 5 (dedicated resources) | 6th Sprint | 2025-10-27 |  | Dedicated and focused sprint for automtion. |  | Wahaj | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression): | Coverage Metrics | E2E/regression coverage (≥70% for core services).
9 | Kekoa | Mazhar Karimi | 1 | 2 (dedicated resources) | 20% | 2025-09-22 |  | Not a lot of automation remains. We will get this done quickly in short time and don't have to wait till the 6th sprint. | Dev Training is required. | Wahaj | Completed |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression): | Product Health | Regression pass rate; flaky test identification and resolution within 1 sprint.
10 | vTrader Web | Mazhar Karimi | 2 | 2 (dedicated resources) | 20% | 2025-09-15 |  | We can immediately start on the automation with a minimum 20% commitment. Don't have to wait for the 6th sprint. | Dev Training is required. | Wahaj | Completed |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
11 | vBate | Mazhar Karimi | 1 | 4 (dedicated resources) | 20% | TBD |  | We can immediately start on the automation with a minimum 20% commitment. Don't have to wait for the 6th sprint. | The automation training is required along with devices. | Wahaj | TBD | Currently, the resources are working on Clever alpha. As soon as vBate resumes, these resources will be available | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression): | Note for Developers: As part of Logiciel’s updated engineering standards, we are tightening how we approach test automation and quality gates. It’s about ensuring our products are secure, reliable, and scalable at enterprise-grade levels. Why this matters Reliability for customers: Automated regression + smoke testing helps us catch issues before customers do. Faster delivery: Less firefighting mean fewer broken builds, and smoother releases. Shared accountability: Quality isn’t just a QA responsibility. It's a shared product responsibility and together, we eliminate gaps. Fewer escaped bugs: Automation reduces manual repetition, gives faster feedback, and lets QA focus on higher-value testing.
12 | OMS API | Mazhar Karimi | 2 | 3 (dedicated resources) | 6th Sprint | 22-Sep-25 (tentative) |  | Dedicated and focused sprint for automtion. |  | Kashaf | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
13 | vHorizon | Mazhar Karimi | 2 | 4 (dedicated resources) | 6th Sprint | 2025-10-27 |  | Dedicated and focused sprint for automtion. |  | Wahaj | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
14 | Funds Approval | Mazhar Karimi | 2 | 1 (dedicated resource) | 6th Sprint | 2025-10-15 |  | Only 1 resource and it would be better to give dedicated sprint time to get more coverage. | there is only resource in FA, who is back-end developer. | Wahaj | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
15 | Risk (Pre Trade Risk) | Faizan Saeed | 2 | 6 (dedicated) | 6th Sprint | 2025-11-17 |  | A dedicated sprint would work fine for Risk |  | Kashaf | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
16 | BOSS | Faizan Saeed | 2 | 14 (13 dedicated and 1 shared) | 20% | 2025-09-22 |  | An entire sprint for BOSS is difficult with too many roadmap items, so 20% every sprint is the way forward. | Dev Training is required. | Wahaj/Talha | Completed |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
17 | Account Monitoring System (AMS - Post Trade Risk) | Faizan Saeed | 2 | 2 (dedicated resources) | 6th Sprint | 2025-11-24 |  | A dedicated sprint would work fine for AMS |  | Wahaj/Kamran | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
18 | vTrader Engine | Farrukh Arshad | 2 | 2 ( 1 dedicated and 1 shared) | 20% | 1st October 2025 |  | Entire sprint is difficult for OE Team because of multiple roadmap items. | Dev Training is required. | Nida Yahya | TBD |  | Automation Cadence Adoption (Target 100%): Coverage Metrics (Target >= 70% for core services): Product Health (smoke + regression):
Note on L1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Kamran Ghaffar Please fill this column.
Note on N1: Metrics Definition Automation Cadence Adoption: % of sprints where automation capacity was honored (6th sprint or 20%). Coverage Metrics: E2E/regression coverage (≥70% for core services). Regression Health: Regression pass rate; flaky test identification and resolution within 1 sprint.
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Muhammad Faizan Rahim Khan Please share the number of resources for all products. Reply: Done
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Muhammad Faizan Rahim Khan Please share the date Reply: Added
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Kamran Ghaffar
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Muhammad Murtaza Pls share the dates for all products.
Note on G7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Muhammad Murtaza Pls share the start date Reply: Hi @Ali Ladhani , I will be discussng this thing with the PO (Musab Mehboob) in my road map meeting which is scheduled for 17th September 2025. Will get back to you after that meeting. Reply: @Muhammad Murtaza Any update on this?
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Muhammad Murtaza Pls share the start date
Note on J8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Kamran Ghaffar Reply: I'll schedule the training once the sprint date finalized @Muhammad Murtaza please update the dates and let me know
Note on G10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Khurram Khalid Iqbal Please revise the dates Reply: Updated. Thanks
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Shahzeb Khan please revise the dates
Note on J12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Kamran Ghaffar Pls schedule trainings Reply: I'll schedule the training once the sprint date finalized @Muhammad Mazhar Karimi Please share the dates so I can act accordingly
Note on J17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Kamran Ghaffar Pls schedule dev trainings Reply: @Syed Wahajuddin Please nominate Talha for the training of the dev resources share the dates